## Town Centre Staveley
Project Name: Town Centre Masterplan/Projects
Risk ref | Risk description | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | successfully concluding the Masterplan in a timely manner | Reputational | Delays or inability to produce Business Case | Regular meetings with BDP and including Critical Friend assistance, Senior Mgt fully briefed | 4 | 5 | 20 | Additional CBC resource & Officer involvement to prepare the Masterplan | 3 | 5 | 15 | CBC
2 | Adequate Consultation to ensure buy in from community & stakeholders | Reputational/Resources | Bad PR and disillusioned community, making it difficult to deliver a robust scheme and develop business cases | Consultation Plan and engagment being developed | 5 | 5 | 25 | Assistance from CBC/Town Deal Team to engage and deliver the consultation plan | 4 | 4 | 16 | CBC
3 | Preparation of Business Case in the time frame (by March 2022) | Reputational/ Financial | Potential loss of Town Deal Funding | Additional CBC resource to prepare Business Cases, but outcome of consultation is important | 3 | 5 | 15 | Senior CBC Officers engaged and regular reviews of resource and capacity | 2 | 4 | 8 | CBC
4
5
6
7
8
9
10

## DRIIVe
Project Name: | DRIIVe
Risk ref | Risk description | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | Impact from reduction in funding or developing a project with less investment | Financial/ Reputational | Financially smaller project | Additional Consultant resource to develop the Busienss Case and Feasibility Study within options apprasials | 3 | 3 | 9 | Continued work on Options appraisal and costings and work with partners to review alternative approaches to deliver outputs | 2 | 2 | 4
2 | Securing Land and site | Legal | delay in project delivery | Discussions ongoing with partners | 2 | 4 | 8 | discussion well advanced | 2 | 2 | 4
3
4
5
6
7
8
9
10

## CSH
Project Name: | Construction Skills Hub
Risk ref | Risk description | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | Getting the right partnership within the construction skills sector | Reputational | reduced quality of training delivery | Feasibility Study complete and Busienss Case developing inc consultation with providers | 3 | 5 | 15 | Further work to procure correct provision | 2 | 2 | 4
2 | Engaging all TD projects to embrace and use CSH | Resources | Limited impact across the area & TD | Regular contact with projects at Sponsor meetings | 2 | 5 | 10 | Build the requriement to engage into project contracts | 1 | 3 | 3
3 | Securing the site for phase I | Legal | Delay in project start | Land owner involved in project, | 2 | 5 | 10 | Planning Service engagement | 1 | 3 | 3
4 | [6 empty] | 0 |  |  |  | 0
5 | [6 empty] | 0 |  |  |  | 0
6
7
8
9
10

## Barrow Hill Mem Hall
Project Name: | Barrow Hill Memorial Hall
Risk ref | Risk description | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | Organisational capacity | Reputational/ Resources / Financial | Failure to develop Business Case and ultimately loss of Project from Town Deal | Project and STD Team meet regularly to ensure appropriate resources are in place | 5 | 5 | 25 | Application for Capacity Funding for support to prepare the Busienss Case | 4 | 4 | 16 | S Redding & CBC - LW
2 | Meeting the deadline for Business Cases | Reputational/ Financial | Failure to develop Business Case and ultimately loss of Project from Town Deal | Project and STD Team meet regularly to ensure appropriate resources are in place | 5 | 5 | 25 | Application for Capacity Funding for support to prepare the Business Case | 4 | 5 | 20 | S Redding & CBC - LW
3 | Securing HLF Match Funding | Reputational/ Financial | A reduced project, viability assessment would need to be produced if only Town Deal funding is available | HLF outline stage I application to be submitted. | 4 | 5 | 20 | viability assessment would need to be produced if only Town Deal funding is available, & Support from Town Deal Team to liaise with HLF if required | 4 | 4 | 16
4 | Securing Planning Permission within the timeline for project development | Legal/ Reputational | Delays in project delivery | Access to Planning Team and support provided | 3 | 4 | 12 | Appointment of additional resource to assist in preparing the planning application | 2 | 3 | 6
5 | Planning permission | Operational | Delay in project | Pre-planning meetings taking place. | 3 | 4 | 12 | Capactiy Funding being sought to support | 2 | 4 | 8
6 | [6 empty] | 0 |  |  |  | 0
7 | [6 empty] | 0 |  |  |  | 0
8 | [6 empty] | 0 |  |  |  | 0
9 | [6 empty] | 0 |  |  |  | 0
10 | [6 empty] | 0 |  |  |  | 0

## Staveley Hall
Project Name: | Staveley Hall
Risk ref |  | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | Cashflow | Financial | Organisation may encounter financial difficulties | Regular contact with TD Team and Capacity funding secured to assist with BC development and costings | 3 | 5 | 15 | Look to use an element of 5% draw down and pre work on business case to address methods to ease cashflow | 3 | 3 | 9
2 | Match Funding | Financial | Project would be much reduced or fail to proceed | Town Council reviewing options | 3 | 5 | 15 | Deliver on the preferred option (following business case options appraisal) | 2 | 3 | 6
3 | Planning permission | Operational | Delay in project | Pre-planning meetings taking place. | 3 | 5 | 15 | Capacity Funding to procure additional support | 2 | 3 | 6
4 | [10 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10

## Rail Station
Project Name: | Staveley Rail Station
Risk ref | Risk description | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | Dovetail Station works with whole Rail Line "bring back my railway" | Reputational, Legal | Project will not progress | Pressure on MHCLG and other Government Depts to raise awareness of the issue | 4 | 5 | 20 | LR (MP) arranging meeting with relevant parties to raise issues and project profile | 3 | 4 | 12
2 | Appointing a Project Manager to develop Business Case by March 2022 | Operational | Deadline for Business Case would be missed | DfT aware of the issue, DCC have identified support and ready to appoint subject to DfT go ahead | 4 | 5 | 20 | As above | 2 | 4 | 8
3 | Deliverability of the whole project in TD timescale | Reputational, Financial | Project will not progress | As above | 4 | 5 | 20 | As above | 3 | 4 | 12
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7
8
9
10

## Hartington Industrial Park
Project Name: | Hartington Industrial Park
Risk ref | Risk description | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | Planning permission | Operational | Delay in project | Pre-planning meetings taking place. | 3 | 5 | 15 | Studies and surveys to be in place based on pre planning site meeting | 2 | 4 | 8
2 | Meeting the deadline for Business Cases (Fast Track Scenario) | Reputational/ Financial | Failure to develop Business Case and ultimately loss of Project from Town Deal | Project and STD Team meet regularly to ensure appropriate resources are in place | 3 | 5 | 15 | Consultants continue to work on fast track basis. Sponsor to discuss dropping the project into 22/23 delivery | 2 | 4 | 8
3
4
5
6
7
8
9
10

## SMWF Skills Academy
Project Name: | SMWFC Skills Academy & Car Park
Risk ref | Risk description | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | Planning Permission for Car Park element | Operational | Delay in project | Awaiting Planning decision | 3 | 5 | 15 | Continued discussions with Planning Service | 1 | 2 | 2
2 | Inflation of costed elements | Financial | project costs will need to be reviewed and phase II may be affected | Review of market costs | 4 | 4 | 16 | Procurement exercise commenced and sponsor working on costing to ensure works are within budget | 2 | 3 | 6
3 | Planning Permission for skills Academy | Operational | Delay in project | Preparations being put in place on build design | 3 | 3 | 9 | Work with Planning Service at early stage to ensure best design option plans are submitted | 2 | 3 | 6
4 | [6 empty] | 0 |  |  |  | 0
5 | [6 empty] | 0 |  |  |  | 0
6
7
8
9
10

## Canal Restoration
Project Name: | Canal Restoration
Risk ref | Risk description | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | NB Canal Trust have produced a thorough Risk Register and shared with the Town Deal Team and shall be regularly reviewed by the Canal Trust Board
2 | Adherence to Planning requirements | Legal & Reputational | Project may be delayed or not progress | Planning Permission is granted and CCT is working through the requirements and supported by Planning Service | 4 | 5 | 20 | Capacity Funding drawn down and request for 5% funding to assist with these requirements | 2 | 4 | 8
3 | Organisational capacity | Resources & Reputational | Failure to deliver project | Own funds have been profiled to this project. Regular contact with TD Team, support provided by CBC Officers, TFDP | 3 | 5 | 15 | Capacity Funding drawn down and request for 5% funding to assist with these requirements | 3 | 3 | 9
4
5
6
7
8
9
10

## Canal Basin
Project Name: | Canal Basin
Risk ref | Risk description | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | Addressing issues raised by Int Prog Board & securing DCC Committee Approval | Resources | Delays in project Business Case submission for Board Approval | Additional staff resource in place. | 3 | 5 | 15 | presentation to DCC committee scheduled | 3 | 3 | 9
2 | Planning Permission - needs to be secured | Legal | project may be delayed or not progress | DCC to meet with CBC Planning Service to discuss requirements of planning permission ahead of submission | 4 | 5 | 20 | Submission of planning permission with permission granted | 3 | 3 | 9
3 | Delivering business case in the time line | Reputational and Financial | Failure to secure TD funding and project does not progress | Draft business case has been produced. DCC project team working to the agreed deadlines and fully aware of timeline, working with TD Team and in regular contact | 3 | 4 | 12 | submission of Final Business Case by agreed deadline | 2 | 3 | 6
4
5
6
7
8
9
10

## Wheels to Work
Project Name: | Wheels to Work
Risk ref | Risk description | Risk area | Risk effect | Existing controls to mitigate the risk | Current risk rating |  |  | Further mitigating action identified and dates for completion | Target risk rating |  |  | Risk lead
[5 empty] | Likelihood | Impact | Risk rating |  | Likelihood | Impact | Risk rating
1 | Capacity of Project Sponsor to prepare Business Case | Resources / Reputational | Failure to develop Business Case and ultimately loss of Project from Town Deal | Meeting with Town Deal Team, DCC and RAD to agree next steps and scope project in detail | 3 | 4 | 12 | DCC can put additional resource to its preparataion, and DCC/Capcatiy Funding cuol dlook to assist RAD should they be required to prepare some of the Stragegic Business Case | 2 | 3 | 6 | DCC
2 | Securing location in Staveley for "office/ collection point" | Operataional | For drop off/tourist uses, delays of this element would be caused | Discussions with potentail locations have begun | 2 | 2 | 4 | Potentail HLC or Staveley Hall, plus initaital project user will recevie the transport and an office may not be required immediately | 1 | 1 | 1
3
4
5
6
7
8
9
10