## Slide 1
Staveley Town Deal Board
16th June 2023
DRIIVe Project Update

## Slide 3
Current Position: Design Milestones
Oct 2022
Appointed Engineer Led Design Team
Nov 2022
Review Stage 2 Maber designs
Jan 2023
Commissioned SI/surveys and reviewed the results
Jan 2023
Appointed a BREEAM consultant
Jan 2023
Coal Authority Permit agreed
Feb 2023
Ground Investigation
Mar 2023
Architects Design Strategy presented to Project Board
Mar 2023
Architect Design evolution, and M&E Design Strategy presented to Project Board
Apr 2023
Civils and Structural Design Strategy presented to project board

## Slide 4: Next Steps
21 June 2023
Formal Pre-application meeting
21 June 2023
RIBA Stage 3 Design Freeze
28 June 2023
Final RIBA Stage 3 designs presented to Project Board
5 July 2023
RIBA Stage 3 report signed off
26 July 2023
Planning submission
1 Aug. 2023
RIBA Stage 4 to commence
1 Sep. 2023
Agree Procurement route for main contractor
25 June 2024
RIBA Stage 5 Construction
1 Sep. 2025
Completion of RIBA Stage 6